## Sheet1
stakeholder_group | awareness | desire | knowledge | ability | reinforcement | key_risk | mitigation_action | delivery_implication
Agents | 4 | 3 | 3 | 5 | 4 | Adoption hesitation: some prefer their own workarounds, others fear job displacement | Pilot group to champion workflow rollout. Performance leniency period as agents learn to utilise portal. | Should this become a backlog item or reporting need?
Team leaders and managers | 5 | 4 | 4 | 4 | 4 | Portal cannot handle 'messy exceptions' effectively | Clear visualisation of exception handling processes | Should manager visibility appear in Phase 1?
Finance | 5 | 3 | 2 | 2 | 2 | Portal lacks observability | Define case status changes thoroughly; define user stories with specific acceptance criteria | What keeps the value case credible?